## Sheet1
CS340 Project - Gaant Chart
Tasks | Start Date | Duration | End Date | Person Doing it | Comment
Finite State Machines | 2009-09-23 | 7 | 2009-09-30 | Todd
Story Board | 2009-09-23 | 8 | 2009-10-01 | Jenny
Basic UI | 2009-09-23 | 7 | 2009-09-30 | Karan
All Relative Images created and polished | 2009-09-29 | 2 | 2009-10-01 | Jenny,Karan
Ship Class Basic | 2009-09-28 | 4 | 2009-10-02 | Todd
Ship Class Movement | 2009-10-02 | 4 | 2009-10-06 | Jenny
Ship Class Reactions | 2009-10-02 | 7 | 2009-10-09 | Todd
Player Ship subclass basic | 2009-10-02 | 7 | 2009-10-09 | Jenny
Basic Enemy Ship subclass | 2009-10-02 | 7 | 2009-10-09 | Karan
Boss Ship SubClass | 2009-10-02 | 7 | 2009-10-09 | Karan
Level Files Formatting | 2009-10-09 | 7 | 2009-10-16 | Todd
Level File Reading | 2009-10-09 | 7 | 2009-10-16 | Karan
Generating content from the Level Files | 2009-10-16 | 7 | 2009-10-23 | Karan
Level (Display) class | 2009-10-23 | 8 | 2009-10-31 | Karan
Displaying score Etc | 2009-10-19 | 5 | 2009-10-24 | Jenny
Implementing Diff weapons | 2009-10-23 | 8 | 2009-10-31 | Jenny
Gameplay implementation | 2009-11-02 | 31 | 2009-12-03 | Karan,Jenny,Todd
Testing | 2009-11-02 | 31 | 2009-12-03 | Karan,Jenny,Todd
Level editor GUI | 2009-10-09 | 21 | 2009-10-30 | Todd | Could Be scrapped
Level editor Options | 2009-10-09 | 21 | 2009-10-30 | Todd | Could Be scrapped
Level editor saving levls | 2009-10-09 | 21 | 2009-10-30 | Todd | Could Be scrapped
Sound | 2009-10-09 | 21 | 2009-10-30 | Jenny | Could Be scrapped
Formulas:
End Date = [Start Date]+[Duration]