## Sheet1
CS340 Project - Gaant Chart
Tasks | Start Date | Duration | End Date | Person Doing it | Comment
Finite State Machines | 2009-09-23 | 7 | 2009-09-30 | Todd
Story Board | 2009-09-23 | 7 | 2009-09-30 | Jenny
All Relative Images created and polished
Basic UI | 2009-09-23 | 7 | 2009-09-30
Ship Class Basic
Ship Class Movement
Ship Class Reactions
Player Ship subclass basic
Basic Enemy Ship subclass
Boss Ship SubClass
Level Files Formatting
Level File Reading
Generating content from the Level Files
Level (Display) class
Displaying score Etc
Implementing Diff weapons
Basic Gameplay
Level editor (maybe) 1 |  |  |  |  | TBD based on time
Level editor (maybe) 2 |  |  |  |  | TBD based on time
Level editor (maybe) 3 |  |  |  |  | TBD based on time
Level editor (maybe) 4 |  |  |  |  | TBD based on time
Level editor (maybe) 5 |  |  |  |  | TBD based on time